## DataConversion
Work Product | Details | Outstanding Issues | Reusable?
Extract process | Extract process from WICM flat files into SQL Server tables using SSIS | N/A | All
Data cleansing of source data | Data cleansing lookup tables for Equipment Manufacturers, Models, Part Manufacturers, Facilities PM data | N/A | All
Lookup value lists | Lookup value lists for EquipmentClass, PM checklists, AssetCategories, EquipmentTypes, etc. | Issues with PM data received from Doug for General Services, which is in the middle of being reworked. Issues with Vendor file, which is in the middle of being reworked. | All, with tweaks depending on target system format
Project Tracking specs and implementation | Conversion guide, numerous specs, and SQL work to configure target entities to enable Project Tracking functionality. | In the middle of implementation, about 80% done. | 50% Concepts, value lists, etc. are reusable, but much of the work is tied to target AssetWorks entities.
Asset Management specs and implementation | Specs, transform logic, SSIS packages to generate load files for all WaterWorks equipment records | Linear assets and service connections not yet fully implemented due to delays in receiving source data. | 30% Definition of which records to be included is reusable. Some of the transform logic is relevant for any system.
Work Management specs and implementation | Specs, transform logic, SSIS packages to generate load files for all WaterWorks work history records | N/A | 30% Definition of which records to be included is reusable. Some of the transform logic is relevant for any system.
Inventory Management specs and implementation | Specs, transform logic, SSIS packages to generate load files for all WaterWorks inventory records (storeroom, trucks with inventory, all part records, etc.) | N/A | 50% Definition of which records to be included is reusable. Some of the transform logic is relevant for any system. This has also included decisions about how to do business in any system, which is relevant.
Procurement specs and implementation | Specs, logic, SSIS packages to generate load files for VendorContract, PurchaseOrder, Requisitions. | N/A | 50% Definition of which records to be included is reusable. Some of the transform logic is relevant for any system. This has also included decisions about how to do business in any system, which is relevant.
Employee Definitions | Data Cleansing process, Spec, logic to generate load file | New Employee Identification Number (EIN) | All with modification on target system
Subsystems | Data Mapping, Specs, logic to generate load files | New Subsystem pending Gap Analysis | 40% Source data mapping can be reused.
Asset Hierarchy | Definition of assets to enable the Facilities Asset Hierarchy, spec, and transform logic to populate load file. | N/A | 80% Hierarchy itself and the assets setup to support the hierarchy are reusable. It is suggested though that if a system has a built in "hierarchy" system, use that instead of using assets to define the hierarchy.
Linear Asset | Spec and transform logic to populate load file for GIS related data | In middle of implementation | The transform logic is reusable if Network Segment ID is used in the new system and the system is integrated to GIS
TAP Extract | Transform logic | Pending full extract | With modification, if the new EAM is not SAP
Gap Analysis | Accounted data fields from WICM that has been mapped, are unused, and are not mapped | Pending implementation of all specs and input from divisions | All with modification to target system format
Tools | Spec and transform logic to populate load file | Pending implementation | It can be used for tool charges with modification
User Group | List of User Group | N/A | Can be used to group users from divisions by role

## Testing
Work Product | Details | Outstanding Issues | Reusable?

## Reporting
Work Product | Details | Outstanding Issues | Reusable?

## Training
Work Product | Details | Outstanding Issues | Reusable?